## Sheet1
Name | Start Date | End Date | Color | Topic
Preparatory phase | 2022-09-19 08:00 | 2023-02-01 17:00 | Intro | Main phases
Introduction | 2022-09-19 08:00 | 2022-11-15 17:00 | Introductory | Introduction subtask 1
State of the art review | 2022-11-15 08:00 | 2023-01-09 17:00 | Introductory | Introduction subtask 2
Python library familiarization | 2023-01-09 08:00 | 2023-02-01 17:00 | Introductory | Introduction subtask 3
Development phase | 2023-02-01 08:00 | 2023-07-03 17:00 | Body of work | Main phases
Data gathering | 2023-02-01 08:00 | 2023-02-22 17:00 | Development | Development subtask 1
EDA | 2023-02-23 08:00 | 2023-03-02 17:00 | Development | Development subtask 2
CXN implementation study | 2023-03-01 08:00 | 2023-03-29 17:00 | Development | Development subtask 3
Small scale experiment | 2023-03-30 08:00 | 2023-06-01 17:00 | Development | Development subtask 4
Setup | 2023-03-30 08:00 | 2023-04-06 17:00 | Experiment | Experiment subtasks 1
Implement classical methodologies | 2023-04-07 08:00 | 2023-04-21 17:00 | Experiment | Experiment subtasks 2
Implement CXN | 2023-04-21 08:00 | 2023-05-18 17:00 | Experiment | Experiment subtasks 3
Validation | 2023-05-18 08:00 | 2023-06-01 17:00 | Experiment | Experiment subtasks 4
Real scale implementation | 2023-06-01 08:00 | 2023-07-03 17:00 | Development | Development subtask 5